## Sheet1
Play | Play name | Item | WATI Approach
Play 1 | Understand what people need | Early in the project, spend time with current and prospective users of the service | Our Product owner spoke to people at Wilton who were impacted by floods and river overflows.
Play 1 | Understand what people need | Use a range of qualitative and quantitative research methods to determine people’s goals, needs, and behaviors; be thoughtful about the time spent | We engaged in interviews to gauge the citizen perspectives.
Play 1 | Understand what people need | Test prototypes of solutions with real people, in the field if possible | We tested our prototype with the users who tried to register to the alerts on the emergency events.
Play 1 | Understand what people need | Document the findings about user goals, needs, behaviors, and preferences | The team was part of collaborative development and their feedback was incorporated into prototype.
Play 1 | Understand what people need | Share findings with the team and agency leadership | The team was part of held at least once a week
Play 1 | Understand what people need | Create a prioritized list of tasks the user is trying to accomplish, also known as "user stories" | We created a Sprint backlog of the user stories and created a minimum value product that can be used by users for the first Sprint.
Play 1 | Understand what people need | As the digital service is being built, regularly test it with potential users to ensure it meets people’s needs | People were engaged in testing the prototype
Play 2 | Address the whole experience, from start to finish | Understand the different points at which people will interact with the service – both online and in person | Mobile Phones and SMS were of higher priority to the users. Users wanted integration with facebook so that the alert can be posted to facebook when they receive it.
Play 2 | Address the whole experience, from start to finish | Identify pain points in the current way users interact with the service, and prioritize these according to user needs | We identified that the timely notification of the alert is critical for the users. Infact the users wanted to receive location based events based on their mobility. For example, if the user is travelling on route to a flood affected area, the user wanted the system to alert that the road is closed etc... We could not implement this feacture in a short Sprint.
Play 2 | Address the whole experience, from start to finish | Design the digital parts of the service so that they are integrated with the offline touch points people use to interact with the service | We identified that the timely notification of the alert is critical for the users. Infact the users wanted to receive location based events based on their mobility. For example, if the user is travelling on route to a flood affected area, the user wanted the system to alert that the road is closed etc... We could not implement this feacture in a short Sprint.
Play 2 | Address the whole experience, from start to finish | Develop metrics that will measure how well the service is meeting user needs at each step of the service | Our design had a user log that tracks when and how the alerts are sent.
Play 3 | Make it simple and intuitive | Use a simple and flexible design style guide for the service. Use the U.S. Web Design Standards as a default | Style guides were used to streamline the communication. The entire development was collaborative owing to the short timeline.
Play 3 | Make it simple and intuitive | Use the design style guide consistently for related digital services | WATI used to existing code base and style guides for rapid application development and refactored existing code. The approach provided a consistent design.
Play 3 | Make it simple and intuitive | Give users clear information about where they are in each step of the process | We ensured that the application is having a simple flow and intuitive. Caters to curent user trands.
Play 3 | Make it simple and intuitive | Follow accessibility best practices to ensure all people can use the service | We made sure that the application is ADA Compliant
Play 3 | Make it simple and intuitive | Provide users with a way to exit and return later to complete the process | The appliction provides sign-out feature to exit the application.
Play 3 | Make it simple and intuitive | Use language that is familiar to the user and easy to understand | We focused on keeping the text, tone, and language as simple and as familiar for the audience as possible.
Play 3 | Make it simple and intuitive | Use language and design consistently throughout the service, including online and offline touch points | we made sure that the user is able to register quickly and efficiently to the alert system.
Play 4 | Build the service using agile and iterative practices | Ship a functioning “minimum viable product” (MVP) that solves a core user need as soon as possible, no longer than three months from the beginning of the project, using a “beta” or “test” period if needed | Prioritized and revised User stories to support an MVP product on initial release. Other features were moved to backlog for later iterations
Play 4 | Build the service using agile and iterative practices | Run usability tests frequently to see how well the service works and identify improvements that should be made | We tested the design concept as well as its usability in order to validate its features as well as functionality
Play 4 | Build the service using agile and iterative practices | Ensure the individuals building the service communicate closely using techniques such as launch meetings, war rooms, daily standups, and team chat tools | We held daily scrum as well as created a project specific to facilitate constant communication the entire team could participate in.User Whatsapp groups for rapid communication among geographically distant teams
Play 4 | Build the service using agile and iterative practices | Keep delivery teams small and focused; limit organizational layers that separate these teams from the business owners | We formed a lean scrum team of 6 people - four from our US office who specialize in user-led design, and 2 from India who build out prototype. Our user research team met directly with our designated users, and participated in the sprints with the dev teams.
Play 4 | Build the service using agile and iterative practices | Release features and improvements multiple times each month | Not applicable for this sprint
Play 4 | Build the service using agile and iterative practices | Create a prioritized list of features and bugs, also known as the “feature backlog” and “bug backlog” | We created a sprint backlog and tracked every day. A Matrix is attached in the Github.
Play 4 | Build the service using agile and iterative practices | Use a source code version control system | We leveraged github's version control and the standard gitflow model for all source code during development.
Play 4 | Build the service using agile and iterative practices | Give the entire project team access to the issue tracker and version control system | All team member have access to Github (or other project repo), and our collaboration tools (e.g., Bitrix)
Play 4 | Build the service using agile and iterative practices | Use code reviews to ensure quality | We conduct reviews as part of code refactoring for this short sprint.
Play 5 | Structure budgets and contracts to support delivery | Budget includes research, discovery, and prototyping activities | We set up a budget covering each of these activities early on, and tracked to it to validate we were maintaining our lean approach.
Play 5 | Structure budgets and contracts to support delivery | Contract is structured to request frequent deliverables, not multi-month milestones | Delivery is estimated and planned based on short term sprints and/or iterations of the product.
Play 5 | Structure budgets and contracts to support delivery | Contract is structured to hold vendors accountable to deliverables | we delivered our vendor profile and prototype with readme on time.
Play 5 | Structure budgets and contracts to support delivery | Contract gives the government delivery team enough flexibility to adjust feature prioritization and delivery schedule as the project evolves | Not applicable for this prototype
Play 5 | Structure budgets and contracts to support delivery | Contract ensures open source solutions are evaluated when technology choices are made | The tools the team used are open source including PHP,MySQL, Linux
Play 5 | Structure budgets and contracts to support delivery | Contract specifies that software and data generated by third parties remains under our control, and can be reused and released to the public as appropriate and in accordance with the law | All code developed for this prototype is released as open source on github.
Play 5 | Structure budgets and contracts to support delivery | Contract allows us to use tools, services, and hosting from vendors with a variety of pricing models, including fixed fees and variable models like “pay-for-what-you-use” services | We leveraged a variety of models, including pay-for-what-you-use hosting from Amazon, and free and open source licensed tools.
Play 5 | Structure budgets and contracts to support delivery | Contract specifies a warranty period where defects uncovered by the public are addressed by the vendor at no additional cost to the government | Not applicable for this prototype
Play 5 | Structure budgets and contracts to support delivery | Contract includes a transition of services period and transition-out plan | Not applicable for this prototype
Play 6 | Assign one leader and hold that person accountable | A product owner has been identified | Subra was assigned as the Product owner and scrum master
Play 6 | Assign one leader and hold that person accountable | All stakeholders agree that the product owner has the authority to assign tasks and make decisions about features and technical implementation details | Subra had final authority on all aspects of the prototype development.
Play 6 | Assign one leader and hold that person accountable | The product owner has a product management background with technical experience to assess alternatives and weigh tradeoffs | Subra has many years of experience with managing large and small scale IT deliveries in the State of California, and elsewhere, and has lead technical development teams.Subra is PMP and CSM.
Play 6 | Assign one leader and hold that person accountable | The product owner has a work plan that includes budget estimates and identifies funding sources | We created a work plan. As this is a short sprint, budget estimates were not an issue for WATI.
Play 6 | Assign one leader and hold that person accountable | The product owner has a strong relationship with the contracting officer | We coordinated with the State's procurement officer for all questions.
Play 7 | Bring in experienced teams | Member(s) of the team have experience building popular, high-traffic digital services | The team had significant prior experience in building open source applicaion web development and integrating with Web services
Play 7 | Bring in experienced teams | Member(s) of the team have experience designing mobile and web applications | The team had significant prior experience in building open source applicaion web/mobile development and integrating with Web services
Play 7 | Bring in experienced teams | Member(s) of the team have experience using automated testing frameworks | Our projects use CI technologies such as Jenkins and standard unit testing libraries to conduct smoke and automated testing in addition to our manual test plans.
Play 7 | Bring in experienced teams | Member(s) of the team have experience with modern development and operations (DevOps) techniques like continuous integration and continuous deployment | We developed using Vagrant (for development), Docker (for production and configuration), Jenkins (for deployment), and Sensu and AWS CloudWatch (for monitoring).
Play 7 | Bring in experienced teams | Member(s) of the team have experience securing digital services | Our team members have worked on financial, medical, and government applications
Play 7 | Bring in experienced teams | A Federal contracting officer is on the internal team if a third party will be used for development work | Not applicable
Play 7 | Bring in experienced teams | A Federal budget officer is on the internal team or is a partner | Not applicable
Play 7 | Bring in experienced teams | The appropriate privacy, civil liberties, and/or legal advisor for the department or agency is a partner | Not applicable
Play 8 | Choose a modern technology stack | Choose software frameworks that are commonly used by private-sector companies creating similar services | We used the same technology choices we do with our private-sector clients, both major companies and startups.
Play 8 | Choose a modern technology stack | Whenever possible, ensure that software can be deployed on a variety of commodity hardware types | The application was deployed on Linux servers on AWS
Play 8 | Choose a modern technology stack | Ensure that each project has clear, understandable instructions for setting up a local development environment, and that team members can be quickly added or removed from projects | The IDE environments ensured that the developers were ableto.
Play 8 | Choose a modern technology stack | Consider open source software solutions at every layer of the stack | All of our tools at every level of the stack are open source.
Play 9 | Deploy in flexible hosting environment | Resources are provisioned on demand | Not applicable for Prototype
Play 9 | Deploy in flexible hosting environment | Resources scale based on real-time user demand | As per AWS
Play 9 | Deploy in flexible hosting environment | Resources are provisioned through an API | As per AWS
Play 9 | Deploy in flexible hosting environment | Resources are available in multiple regions | As per AWS
Play 9 | Deploy in flexible hosting environment | We only pay for resources we use | As per AWS
Play 9 | Deploy in flexible hosting environment | Static assets are served through a content delivery network | Not applicable for Prototype
Play 9 | Deploy in flexible hosting environment | Application is hosted on commodity hardware | All virtualized
Play 10 | Automate testing and deployments | Create automated tests that verify all user-facing functionality | Unit tests run against APIs
Play 10 | Automate testing and deployments | Create unit and integration tests to verify modules and components | Unit tests built into the server code
Play 10 | Automate testing and deployments | Run tests automatically as part of the build process | Unit tests run during deployment
Play 10 | Automate testing and deployments | Perform deployments automatically with deployment scripts, continuous delivery services, or similar techniques | Deployments are automatically kicked off by Jenkins, pulled from the latest develop branch, built into a container and deployed
Play 10 | Automate testing and deployments | Conduct load and performance tests at regular intervals, including before public launch | Not applicable for Prototype
Play 11 | Manage security and privacy through reusable processes | Contact the appropriate privacy or legal officer of the department or agency to determine whether a System of Records Notice (SORN), Privacy Impact Assessment, or other review should be conducted | Not applicable for Prototype
Play 11 | Manage security and privacy through reusable processes | Determine, in consultation with a records officer, what data is collected and why, how it is used or shared, how it is stored and secured, and how long it is kept | Not applicable for Prototype
Play 11 | Manage security and privacy through reusable processes | Determine, in consultation with a privacy specialist, whether and how users are notified about how personal information is collected and used, including whether a privacy policy is needed and where it should appear, and how users will be notified in the event of a security breach | Not applicable for Prototype
Play 11 | Manage security and privacy through reusable processes | Consider whether the user should be able to access, delete, or remove their information from the service | Not applicable for Prototype
Play 11 | Manage security and privacy through reusable processes | “Pre-certify” the hosting infrastructure used for the project using FedRAMP | Not applicable for Prototype
Play 11 | Manage security and privacy through reusable processes | Use deployment scripts to ensure configuration of production environment remains consistent and controllable | Dockerfiles and AWS resources (such as VPC Security Groups) used to control this. In a larger project, other configuration tools (e.g., Chef, Puppet, or Ansible) would also be used
Play 12 | Use data to drive decisions | Monitor system-level resource utilization in real time | Both AWS CloudWatch and Senu (plus local app and Docker logging) used for performance monitoring
Play 12 | Use data to drive decisions | Monitor system performance in real-time (e.g. response time, latency, throughput, and error rates) | Both AWS CloudWatch and Senu (plus local app and Docker logging) used for performance monitoring
Play 12 | Use data to drive decisions | Ensure monitoring can measure median, 95th percentile, and 98th percentile performance | Not applicable for Prototype
Play 12 | Use data to drive decisions | Create automated alerts based on this monitoring | CloudWatch push notifications enabled for system degradation or system down conditions
Play 12 | Use data to drive decisions | Track concurrent users in real-time, and monitor user behaviors in the aggregate to determine how well the service meets user needs | Normally, we integrate analytics services such as Omniture to cover detailed user analytics
Play 12 | Use data to drive decisions | Publish metrics internally | Not applicable for Prototype
Play 12 | Use data to drive decisions | Publish metrics externally | Not applicable for Prototype
Play 12 | Use data to drive decisions | Use an experimentation tool that supports multivariate testing in production | Not applicable for Prototype
Play 13 | Default to open | Offer users a mechanism to report bugs and issues, and be responsive to these reports | Not applicable for Prototype
Play 13 | Default to open | Provide datasets to the public, in their entirety, through bulk downloads and APIs (application programming interfaces) | We leveraged the government's publically available API, which provides the bulk of the data used in this app.
Play 13 | Default to open | Ensure that data from the service is explicitly in the public domain, and that rights are waived globally via an international public domain dedication, such as the “Creative Commons Zero” waiver | The non-test data used for this service comes from a public API provided by the State, and is thus explicitly in the public domain.
Play 13 | Default to open | Catalog data in the agency’s enterprise data inventory and add any public datasets to the agency’s public data listing | As this is a prototype, we aren't adding data to any agency's enterprise data inventory.
Play 13 | Default to open | Ensure that we maintain the rights to all data developed by third parties in a manner that is releasable and reusable at no cost to the public | We are leveraging the publically available API provided by the State for this prototype, which is freely available for use.
Play 13 | Default to open | Ensure that we maintain contractual rights to all custom software developed by third parties in a manner that is publishable and reusable at no cost | All code developed for this prototype is released as open source on github.
Play 13 | Default to open | When appropriate, create an API for third parties and internal users to interact with the service directly | We leveraged the government's publically available FFA API, which provides the bulk of the data used in this app.
Play 13 | Default to open | When appropriate, publish source code of projects or components online | All code developed for this prototype is released as open source on github.
Play 13 | Default to open | When appropriate, share your development process and progress publicly | Artifacts outlining our development process and progress were deployed to our public github repository

## Plays
Play | Name
Play 1 | Understand what people need
Play 2 | Address the whole experience, from start to finish
Play 3 | Make it simple and intuitive
Play 4 | Build the service using agile and iterative practices
Play 5 | Structure budgets and contracts to support delivery
Play 6 | Assign one leader and hold that person accountable
Play 7 | Bring in experienced teams
Play 8 | Choose a modern technology stack
Play 9 | Deploy in flexible hosting environment
Play 10 | Automate testing and deployments
Play 11 | Manage security and privacy through reusable processes
Play 12 | Use data to drive decisions
Play 13 | Default to open